## Master Compliance Matrix
MASTER COMPLIANCE MATRIX
Saudi Enterprise Cybersecurity Transformation Program ¦ NCA ECC / CSCC / ISO 27001 / NDMO Aligned
Framework | Domain | Subdomain | Control ID | Control Name | Detailed Description | Risk Level | Priority | Technology Category | Recommended Technology | Vendor | Compliance Status | Implementation Phase | Comments
NCA ECC | 1. Cybersecurity Governance | 1-1 Cybersecurity Strategy | ECC-1-1-1 | Cybersecurity Strategy | Establish and approve cybersecurity strategy aligned with national regulations | Critical | P1 | GRC | GRC Platform | CyberArrow | Not Started | Phase 1 | Mandatory for NCA compliance
NCA ECC | 1. Cybersecurity Governance | 1-1 Cybersecurity Strategy | ECC-1-1-2 | Cybersecurity Policy | Develop and approve comprehensive cybersecurity policies | Critical | P1 | GRC | Policy Management | CyberArrow | Not Started | Phase 1
NCA ECC | 1. Cybersecurity Governance | 1-2 Cybersecurity Management | ECC-1-2-1 | Cybersecurity Roles & Responsibilities | Define cybersecurity roles and assign responsibilities | High | P1 | GRC | GRC Platform | CyberArrow | Not Started | Phase 1
NCA ECC | 1. Cybersecurity Governance | 1-2 Cybersecurity Management | ECC-1-2-2 | Cybersecurity Risk Management | Implement cybersecurity risk management process | Critical | P1 | GRC | Risk Management | CyberArrow | Not Started | Phase 1
NCA ECC | 1. Cybersecurity Governance | 1-3 Compliance | ECC-1-3-1 | Regulatory Compliance | Ensure compliance with NCA, SAMA, NDMO regulations | Critical | P1 | GRC | Compliance Management | CyberArrow | Not Started | Phase 1
NCA ECC | 1. Cybersecurity Governance | 1-4 Cybersecurity Awareness | ECC-1-4-1 | Security Awareness Training | Implement security awareness and training program | High | P1 | Security Awareness | Security Awareness Platform | Proofpoint | Not Started | Phase 2
NCA ECC | 2. Cybersecurity Defense | 2-1 Asset Management | ECC-2-1-1 | Asset Inventory | Maintain comprehensive inventory of all IT and OT assets | Critical | P1 | Asset Management | CMDB / Asset Discovery | Fortinet FortiNAC | Not Started | Phase 1
NCA ECC | 2. Cybersecurity Defense | 2-2 Identity & Access Management | ECC-2-2-1 | Identity Management | Implement centralized identity management system | Critical | P1 | IAM | Identity Governance | Fortinet FortiAuthenticator | Not Started | Phase 1 | 802.1X / RADIUS
NCA ECC | 2. Cybersecurity Defense | 2-2 Identity & Access Management | ECC-2-2-2 | Privileged Access Management | Implement PAM solution for privileged accounts | Critical | P1 | PAM | PAM Solution | Fortinet FortiPAM | Not Started | Phase 1 | Zero Trust aligned
NCA ECC | 2. Cybersecurity Defense | 2-2 Identity & Access Management | ECC-2-2-3 | Multi-Factor Authentication | Enforce MFA for all critical systems | Critical | P1 | MFA | MFA Tokens | Fortinet FortiToken | Not Started | Phase 1
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-1 | Network Security | Implement network security controls including NGFW | Critical | P1 | NGFW | Next-Gen Firewall | Fortinet FortiGate | Not Started | Phase 1 | Defense in Depth
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-2 | Network Segmentation | Implement network segmentation and micro-segmentation | Critical | P1 | Segmentation | NGFW + Switch Segmentation | Fortinet FortiGate/FortiSwitch | Not Started | Phase 1 | VRF/VLAN based
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-3 | Intrusion Prevention | Deploy IPS for network threat detection | Critical | P1 | IPS | Inline IPS | Fortinet FortiGate IPS | Not Started | Phase 1
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-4 | Web Application Firewall | Deploy WAF for web application protection | High | P1 | WAF | WAF Appliance | Fortinet FortiWeb | Not Started | Phase 2
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-5 | Email Security | Implement email security gateway | High | P1 | Email Security | Email Security Gateway | Fortinet FortiMail | Not Started | Phase 2
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-6 | Endpoint Security | Deploy endpoint detection and response | Critical | P1 | EDR | EDR/XDR Solution | Fortinet FortiEDR | Not Started | Phase 1 | Air-gap compatible
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-7 | Data Loss Prevention | Implement DLP for data at rest, in motion, in use | Critical | P1 | DLP | DLP Solution | Fortinet FortiDLP | Not Started | Phase 2
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-8 | Sandbox / APT Protection | Deploy sandboxing for advanced threat protection | High | P2 | Sandbox | Sandbox Appliance | Fortinet FortiSandbox | Not Started | Phase 2 | Air-gap compatible
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-9 | Network Access Control | Implement 802.1X NAC for all network ports | Critical | P1 | NAC | NAC Solution | Fortinet FortiNAC | Not Started | Phase 1 | Zero Trust
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-10 | Wireless Security | Secure wireless access with WPA3 and WIPS | High | P1 | Wireless | Enterprise Wireless | Fortinet FortiAP | Not Started | Phase 1
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-11 | Secure Remote Access | Implement ZTNA/VPN for secure remote access | High | P1 | SASE/ZTNA | SASE Platform | Fortinet FortiSASE | Not Started | Phase 2
NCA ECC | 2. Cybersecurity Defense | 2-3 Information System Protection | ECC-2-3-12 | Air-Gap Media Security | Deploy secure file transfer for air-gapped environments | Critical | P1 | Media Security | Kiosk / Media Scanning | OPSWAT MetaDefender | Not Started | Phase 1 | Mandatory for air-gap
NCA ECC | 2. Cybersecurity Defense | 2-4 Encryption | ECC-2-4-1 | Data Encryption | Implement encryption for data at rest and in transit | Critical | P1 | Encryption | HSM / Encryption | Thales | Not Started | Phase 1
NCA ECC | 3. Cybersecurity Resilience | 3-1 BC & DR | ECC-3-1-1 | Business Continuity | Develop and test BCP/DR plans | High | P2 | BC/DR | BC/DR Platform | N/A | Not Started | Phase 3
NCA ECC | 3. Cybersecurity Resilience | 3-2 Incident Response | ECC-3-2-1 | Incident Response Plan | Establish incident response procedures | Critical | P1 | SOAR | SOAR Platform | Fortinet FortiSOAR | Not Started | Phase 2
NCA ECC | 3. Cybersecurity Resilience | 3-3 Threat Management | ECC-3-3-1 | Threat Intelligence | Implement threat intelligence feeds and analysis | High | P2 | Threat Intel | Threat Intel Platform | Recorded Future | Not Started | Phase 2
NCA ECC | 4. Third Party Security | 4-1 Vendor Risk | ECC-4-1-1 | Third Party Risk Management | Assess and manage third-party cybersecurity risks | High | P2 | GRC | TPRM Module | CyberArrow | Not Started | Phase 2
NCA ECC | 5. ICS/OT Security | 5-1 OT Protection | ECC-5-1-1 | OT Network Security | Implement OT/ICS specific security controls | Critical | P1 | OT Security | OT NDR/IDS | Nozomi Networks | Not Started | Phase 2 | Purdue Model
NCA ECC | 5. ICS/OT Security | 5-1 OT Protection | ECC-5-1-2 | IT/OT Segregation | Enforce strict IT/OT network segregation | Critical | P1 | Segmentation | NGFW IT/OT Boundary | Fortinet FortiGate | Not Started | Phase 1 | DMZ between IT/OT
NCA CSCC | 1. Cybersecurity Governance | 1-1 Strategy | CSCC-1-1 | Cloud Security Strategy | Define cloud security strategy and governance | High | P2 | Cloud Security | CASB/CSPM | Netskope | Not Started | Phase 3
NCA CSCC | 2. Cloud Protection | 2-1 Cloud IAM | CSCC-2-1 | Cloud Identity Management | Implement cloud-native IAM with MFA | High | P2 | Cloud IAM | Cloud IAM/SSO | Fortinet FortiAuthenticator | Not Started | Phase 3
NCA CSCC | 2. Cloud Protection | 2-2 Data Protection | CSCC-2-2 | Cloud Data Classification | Classify and protect cloud data | High | P2 | Data Classification | DLP/Classification | Forcepoint | Not Started | Phase 3
NCA CSCC | 2. Cloud Protection | 2-3 Network Security | CSCC-2-3 | Cloud Network Security | Implement cloud network security controls | High | P2 | Cloud Firewall | Cloud NGFW | Fortinet FortiGate-VM | Not Started | Phase 3
NCA CSCC | 3. Cloud Monitoring | 3-1 Logging | CSCC-3-1 | Cloud Logging & Monitoring | Centralize cloud security event logging | High | P2 | SIEM | Cloud SIEM Integration | Fortinet FortiSIEM | Not Started | Phase 3
ISO 27001 | A.5 Information Security Policies | A.5.1 | ISO-A.5.1 | Information Security Policy | Management direction for information security | Critical | P1 | GRC | Policy Framework | CyberArrow | Not Started | Phase 1
ISO 27001 | A.6 Organization of IS | A.6.1 | ISO-A.6.1 | Internal Organization | Roles and responsibilities for IS | High | P1 | GRC | GRC Platform | CyberArrow | Not Started | Phase 1
ISO 27001 | A.7 Human Resource Security | A.7.2 | ISO-A.7.2 | During Employment | Security awareness and training | High | P1 | Security Awareness | Training Platform | KnowBe4 | Not Started | Phase 2
ISO 27001 | A.8 Asset Management | A.8.1 | ISO-A.8.1 | Responsibility for Assets | Asset inventory and classification | Critical | P1 | Asset Management | Asset Discovery | Fortinet FortiNAC | Not Started | Phase 1
ISO 27001 | A.9 Access Control | A.9.1 | ISO-A.9.1 | Business Requirements of AC | Access control policy | Critical | P1 | IAM | IAM/PAM | Fortinet FortiAuthenticator | Not Started | Phase 1
ISO 27001 | A.9 Access Control | A.9.4 | ISO-A.9.4 | System and Application AC | MFA and strong authentication | Critical | P1 | MFA | Multi-Factor Auth | Fortinet FortiToken | Not Started | Phase 1
ISO 27001 | A.10 Cryptography | A.10.1 | ISO-A.10.1 | Cryptographic Controls | Encryption policy and implementation | Critical | P1 | Encryption | HSM/Encryption | Thales | Not Started | Phase 1
ISO 27001 | A.12 Operations Security | A.12.4 | ISO-A.12.4 | Logging and Monitoring | Event logging and monitoring | Critical | P1 | SIEM | SIEM/Log Management | Fortinet FortiSIEM | Not Started | Phase 1
ISO 27001 | A.12 Operations Security | A.12.6 | ISO-A.12.6 | Technical Vulnerability Mgmt | Vulnerability scanning and management | High | P1 | Vulnerability Mgmt | VA Scanner | Qualys | Not Started | Phase 2
ISO 27001 | A.13 Communications Security | A.13.1 | ISO-A.13.1 | Network Security Management | Network segmentation and controls | Critical | P1 | Network Security | NGFW/Segmentation | Fortinet FortiGate | Not Started | Phase 1
ISO 27001 | A.14 System Acquisition | A.14.2 | ISO-A.14.2 | Security in Development | Secure SDLC and code review | Medium | P3 | AppSec | SAST/DAST | Black Duck | Not Started | Phase 3
ISO 27001 | A.16 IS Incident Management | A.16.1 | ISO-A.16.1 | Incident Management | Incident response procedures | Critical | P1 | SOAR | Incident Response | Fortinet FortiSOAR | Not Started | Phase 2
ISO 27001 | A.17 Business Continuity | A.17.1 | ISO-A.17.1 | IS Continuity | Business continuity planning | High | P2 | BC/DR | BC/DR | N/A | Not Started | Phase 3
ISO 27001 | A.18 Compliance | A.18.1 | ISO-A.18.1 | Compliance with Legal Reqs | Regulatory compliance management | Critical | P1 | GRC | Compliance Platform | CyberArrow | Not Started | Phase 1
NDMO | Data Governance | DG-1 | NDMO-DG-1 | Data Classification | Classify organizational data per NDMO framework | Critical | P1 | Data Classification | DLP/Classification | Forcepoint | Not Started | Phase 2
NDMO | Data Governance | DG-2 | NDMO-DG-2 | Data Protection | Implement data protection controls | Critical | P1 | DLP | DLP Solution | Fortinet FortiDLP | Not Started | Phase 2
NDMO | Data Governance | DG-3 | NDMO-DG-3 | Data Sharing | Control data sharing with third parties | High | P2 | DRM | Digital Rights Mgmt | Seclore | Not Started | Phase 3
NDMO | Data Privacy | DP-1 | NDMO-DP-1 | Privacy Controls | Implement privacy controls per PDPL | High | P2 | Privacy | Privacy Platform | CyberArrow | Not Started | Phase 2
NDMO | Data Quality | DQ-1 | NDMO-DQ-1 | Data Quality Management | Ensure data quality and integrity | Medium | P3 | Data Quality | Data Governance Tool | N/A | Not Started | Phase 3

## Technology Mapping Matrix
TECHNOLOGY MAPPING & VENDOR SELECTION MATRIX
Saudi Enterprise Cybersecurity Transformation Program ¦ NCA ECC / CSCC / ISO 27001 / NDMO Aligned
Framework | Control ID | Control Description | Technology Category | Technology | Strategic Vendor | Non-Strategic Vendor | Product Name | Part Number | Qty | Unit Price (USD) | Total Price (USD) | Sizing Notes | HA Required | Air-Gapped Compatible | Zero Trust Compatible | Comments
NCA ECC | ECC-2-3-1 | Network Perimeter Security - NGFW | NGFW | Next-Generation Firewall (Core/DC) | Fortinet |  | FortiGate-1800F HW+3Y UTP Bundle | FG-1800F-BDL-950-36 | 2 | 212825.16 | 425650.32 | DC Core Firewall, HA Pair | Yes | Yes | Yes | Enterprise Protection Bundle
NCA ECC | ECC-2-3-1 | Network Perimeter Security - NGFW | NGFW | Next-Generation Firewall (Internet Edge) | Fortinet |  | FortiGate-900G HW+3Y UTP Bundle | FG-900G-BDL-950-36 | 2 | 138240 | 276480 | Internet Edge HA Pair | Yes | No | Yes
NCA ECC | ECC-2-3-1 | Network Perimeter Security - NGFW | NGFW | Next-Generation Firewall (Distribution) | Fortinet |  | FortiGate-400F HW+3Y UTP Bundle | FG-400F-BDL-950-36 | 4 | 58411.32 | 233645.28 | Campus Distribution, 2 per site | Yes | Yes | Yes | East-West inspection
NCA ECC | ECC-2-3-1 | Network Perimeter Security - NGFW | NGFW | Branch Firewall | Fortinet |  | FortiGate-120G HW+3Y UTP Bundle | FG-120G-BDL-950-36 | 10 | 13824 | 138240 | Branch offices | Yes | No | Yes | SD-WAN capable
NCA ECC | ECC-2-3-2 | Network Segmentation | Network Infrastructure | Access Layer Switch (48-port PoE+) | Fortinet |  | FortiSwitch-248E-FPOE | FS-248E-FPOE | 40 | 3930 | 157200 | Access layer, PoE for AP/phones | No | Yes | Yes
NCA ECC | ECC-2-3-2 | Network Segmentation | Network Infrastructure | Access Layer Switch (24-port PoE+) | Fortinet |  | FortiSwitch-124F-FPOE | FS-124F-FPOE | 20 | 2010 | 40200 | Branch/small IDF | No | Yes | Yes
NCA ECC | ECC-2-3-2 | Network Segmentation | Network Infrastructure | Distribution/Core Switch (48-port 10G) | Fortinet |  | FortiSwitch-1048G | FS-1048G | 4 | 32592 | 130368 | Core aggregation | Yes | Yes | Yes
NCA ECC | ECC-2-3-10 | Wireless Security | Wireless | Enterprise Access Point (Wi-Fi 6E) | Fortinet |  | FortiAP-23JF-A | FAP-23JF-A | 80 | 568.8 | 45504 | Indoor AP, 1 per 25 users | No | No | Yes | WPA3 Enterprise
NCA ECC | ECC-2-3-9 | Network Access Control | NAC | NAC Controller Appliance | Fortinet | Forescout | FortiNAC-CA-500F | FNC-CA-500F | 2 | 16380 | 32760 | Up to 15000 endpoints, HA | Yes | Yes | Yes | 802.1X enforcement
NCA ECC | ECC-2-3-9 | Network Access Control | NAC | NAC 3Y Support | Fortinet |  | FortiNAC-CA-500F 3Y FC Premium | FC-10-NF500-247-02-36 | 2 | 9828 | 19656
NCA ECC | ECC-2-2-1 | Identity & Access Management | IAM | Authentication Server | Fortinet | One Identity | FortiAuthenticator Cloud 3Y (500-1999) | FC3-10-ACCLD-511-02-36 | 200 | 129.6 | 25920 | Per-user 3Y subscription | No | No | Yes | RADIUS/LDAP/SAML
NCA ECC | ECC-2-2-2 | Privileged Access Management | PAM | PAM Appliance | Fortinet | BeyondTrust | FortiPAM-1000G | FPA-1000G | 2 | 70800 | 141600 | Up to 50 concurrent users, HA | Yes | Yes | Yes | Session recording
NCA ECC | ECC-2-2-2 | Privileged Access Management | PAM | PAM 3Y AV+DLP | Fortinet |  | FortiPAM-1000G 3Y AV+DLP | FC-10-PA1KG-681-02-36 | 2 | 42480 | 84960
NCA ECC | ECC-2-2-3 | Multi-Factor Authentication | MFA | MFA Tokens (Software) | Fortinet |  | FortiToken Mobile License (100 users) | FTM-ELIC-100 | 4 | 9165.6 | 36662.4 | 400 tokens for initial deployment | No | Yes | Yes
NCA ECC | ECC-2-3-6 | Endpoint Detection & Response | EDR | EDR Solution (On-Prem, 500 endpoints, 3Y) | Fortinet | CrowdStrike | FortiEDR D&P&R On-Prem 3Y (500ep) | FC2-10-FEDR1-352-01-36 | 1 | 129600 | 129600 | 500 endpoints initial | No | Yes | Yes | On-premise deployment
NCA ECC | ECC-2-3-6 | Endpoint VPN/ZTNA Agent | Endpoint | VPN/ZTNA Agent (500 endpoints, 3Y) | Fortinet |  | FortiClient VPN/ZTNA 3Y (500ep) | FC2-10-EMS05-428-01-36 | 1 | 24969.6 | 24969.6 |  | No | No | Yes
NCA ECC | ECC-2-3-5 | Email Security | Email Security | Email Security Gateway | Fortinet |  | FortiMail-200F HW+3Y Base Bundle | FML-200F-BDL-640-36 | 2 | 14931 | 29862 | HA pair, up to 600 users | Yes | Yes | No | AS/AV/DLP
NCA ECC | ECC-2-3-4 | Web Application Firewall | WAF | WAF Appliance | Fortinet |  | FortiWeb-100F HW+3Y Standard | FWB-100F-BDL-934-12 | 2 | 25200 | 50400 | HA pair (1Y bundle, extend) | Yes | Yes | Yes | OWASP Top 10
NCA ECC | ECC-2-3-8 | Sandbox / APT Protection | Sandbox | Sandbox Appliance | Fortinet |  | FortiSandbox-500G | FSA-500G | 1 | 30000 | 30000 | SMB appliance for initial | No | Yes | Yes | Air-gap capable
NCA ECC | ECC-2-3-7 | Data Loss Prevention | DLP | DLP Solution (500 endpoints, 3Y) | Fortinet | Forcepoint | FortiDLP Core 3Y (500-1999ep) | FC3-10-DLPEP-1097-02-36 | 500 | 162 | 81000 | Per endpoint, 3Y | No | No | Yes
NCA ECC | ECC-3-2-1 | Security Monitoring - SIEM | SIEM | SIEM All-in-One Appliance | Fortinet |  | FortiSIEM-2200G | FSM-2200G | 1 | 47040 | 47040 | All-in-one appliance | No | Yes | Yes
NCA ECC | ECC-3-2-1 | Security Monitoring - SIEM | SIEM | SIEM Collector | Fortinet |  | FortiSIEM-500G Collector | FSM-500G | 2 | 15600 | 31200 | Remote log collection | No | Yes | Yes
NCA ECC | ECC-3-2-1 | Security Orchestration | SOAR | SOAR Platform (Cloud, 3Y) | Fortinet |  | FortiSOAR Cloud Enterprise 3Y | FC-10-SRCLD-385-02-36 | 1 | 329911.2 | 329911.2 | Enterprise Edition | No | No | Yes | Playbook automation
NCA ECC | ECC-3-3-1 | Network Detection & Response | NDR | NDR Appliance | Fortinet | Vectra | FortiNDR-1000F HW+3Y Bundle | FNR-1000F-BDL-331-36 | 1 | 219300 | 219300 | AI-based detection | No | Yes | Yes
NCA ECC | ECC-2-3-12 | Air-Gap Media Security | Media Security | Secure Media Kiosk | OPSWAT |  | MetaDefender Kiosk | MDF-KIOSK | 4 | 0 | 0 | Pricing TBD, contact OPSWAT | No | Yes | No | USB/media scanning
NCA ECC | ECC-2-1-1 | Centralized Logging | Log Management | Log Analyzer Appliance | Fortinet |  | FortiAnalyzer-300G HW+3Y Enterprise | FAZ-300G-BDL-1263-36 | 1 | 0 | 0 | Centralized logging | No | Yes | Yes | Check pricing
NCA ECC | ECC-2-1-1 | Centralized Management | Management | Centralized FW Management | Fortinet |  | FortiManager-200G | FMG-200G | 1 | 19862.4 | 19862.4 | Manages up to 30 devices | No | Yes | Yes
NCA ECC | ECC-2-3-11 | Secure Access Service Edge | SASE | SASE User License (500 users, 3Y) | Fortinet | Zscaler | FortiSASE Standard 3Y (500-1999) | FC3-10-EMS05-547-02-36 | 200 | 288 | 57600 | Per user, 3Y | No | No | Yes | ZTNA+SWG+CASB
NCA ECC | ECC-2-4-1 | Encryption & Key Management | Encryption | HSM Appliance | Thales | Entrust | Thales Luna Network HSM | LUNA-HSM | 2 | 0 | 0 | Pricing TBD | Yes | Yes | Yes | FIPS 140-2 L3
NCA ECC | ECC-5-1-1 | OT/ICS Security | OT Security | OT Network Monitor | Nozomi | Dragos | Nozomi Guardian | NOZOMI-GUARD | 2 | 0 | 0 | Pricing TBD | Yes | Yes | No | Purdue Model L3.5
ISO 27001 | ISO-A.12.6 | Vulnerability Management | Vulnerability Mgmt | VA Scanner | Qualys | Tenable | Qualys VMDR | QUALYS-VMDR | 1 | 0 | 0 | SaaS, pricing TBD | No | No | Yes
NCA ECC | ECC-1-4-1 | Security Awareness | Security Awareness | Training Platform | Proofpoint | KnowBe4 | Proofpoint SAT | PROOFPOINT-SAT | 1 | 0 | 0 | SaaS, per user | No | No | No
NCA ECC | ECC-1-3-1 | GRC Platform | GRC | GRC/Compliance Platform | CyberArrow | Jethur | CyberArrow GRC | CYBERARROW-GRC | 1 | 0 | 0 | SaaS, pricing TBD | No | No | No | NCA ECC/CSCC mapped
NDMO | NDMO-DG-3 | Digital Rights Management | DRM | DRM Solution | Seclore |  | Seclore Rights Mgmt | SECLORE-DRM | 1 | 0 | 0 | Pricing TBD | No | Yes | No
NCA ECC | ECC-2-3-1 | DDoS Protection | DDoS | DDoS Protection | A10 | Netscout | A10 Thunder TPS | A10-TPS | 2 | 0 | 0 | Pricing TBD | Yes | No | No
ISO 27001 | ISO-A.14.2 | Application Security Testing | AppSec | SAST/DAST Platform | Black Duck | Veracode | Black Duck SAST | BLACKDUCK-SAST | 1 | 0 | 0 | Pricing TBD | No | No | No
NCA ECC | ECC-2-3-2 | Network Packet Broker | NPB | Network Visibility | Gigamon |  | Gigamon GigaVUE | GIGAMON-GVUE | 2 | 0 | 0 | Pricing TBD | Yes | Yes | Yes
NCA ECC | ECC-2-1-1 | UEM / Device Management | UEM | Unified Endpoint Mgmt | Ivanti |  | Ivanti Neurons for UEM | IVANTI-UEM | 1 | 0 | 0 | Pricing TBD | No | No | No

## Bill of Materials (BOM)
CONSOLIDATED BILL OF MATERIALS (BOM)
Saudi Enterprise Cybersecurity Transformation Program ¦ NCA ECC / CSCC / ISO 27001 / NDMO Aligned
# | Category | Vendor | Product | Part Number | Qty | Unit Price (USD) | Total Price (USD) | Subscription Term | Support Level | Deployment Zone | Notes
1 | NGFW - DC Core | Fortinet | FortiGate-1800F HW+3Y UTP | FG-1800F-BDL-950-36 | 2 | 212825.16 | 425650.32 | 3 Year | FortiCare Premium | Enterprise DC | HA Pair - DC Core
2 | NGFW - Internet Edge | Fortinet | FortiGate-900G HW+3Y UTP | FG-900G-BDL-950-36 | 2 | 138240 | 276480 | 3 Year | FortiCare Premium | Internet Edge | HA Pair
3 | NGFW - Distribution | Fortinet | FortiGate-400F HW+3Y UTP | FG-400F-BDL-950-36 | 4 | 58411.32 | 233645.28 | 3 Year | FortiCare Premium | Campus Distribution | 2 HA pairs
4 | NGFW - Branch | Fortinet | FortiGate-120G HW+3Y UTP | FG-120G-BDL-950-36 | 10 | 13824 | 138240 | 3 Year | FortiCare Premium | Branch | SD-WAN capable
5 | Access Switch 48P | Fortinet | FortiSwitch-248E-FPOE | FS-248E-FPOE | 40 | 3930 | 157200 | N/A | FortiCare | Access Layer | 48-port PoE+
6 | Access Switch 24P | Fortinet | FortiSwitch-124F-FPOE | FS-124F-FPOE | 20 | 2010 | 40200 | N/A | FortiCare | Access Layer | 24-port PoE+
7 | Core Switch | Fortinet | FortiSwitch-1048G | FS-1048G | 4 | 32592 | 130368 | N/A | FortiCare | Core/Distribution | 48x 10G SFP+
8 | Wireless AP | Fortinet | FortiAP-23JF-A | FAP-23JF-A | 80 | 568.8 | 45504 | N/A | FortiCare | Access Layer | Wi-Fi 6E
9 | NAC Controller | Fortinet | FortiNAC-CA-500F | FNC-CA-500F | 2 | 16380 | 32760 | N/A | FortiCare | Security | HA Pair
10 | NAC Support | Fortinet | FortiNAC 3Y FC Premium | FC-10-NF500-247-02-36 | 2 | 9828 | 19656 | 3 Year | FortiCare Premium | Security
11 | IAM - Authentication | Fortinet | FortiAuthenticator Cloud 3Y | FC3-10-ACCLD-511-02-36 | 200 | 129.6 | 25920 | 3 Year | FortiCare Premium | Security | Per user
12 | PAM Appliance | Fortinet | FortiPAM-1000G | FPA-1000G | 2 | 70800 | 141600 | N/A | FortiCare | Security | HA Pair, 50 users
13 | PAM AV+DLP | Fortinet | FortiPAM-1000G 3Y AV+DLP | FC-10-PA1KG-681-02-36 | 2 | 42480 | 84960 | 3 Year | FortiCare Premium | Security
14 | MFA Tokens | Fortinet | FortiToken Mobile (100) | FTM-ELIC-100 | 4 | 9165.6 | 36662.4 | Perpetual | N/A | Security | 400 tokens
15 | EDR | Fortinet | FortiEDR D&P&R 3Y (500ep) | FC2-10-FEDR1-352-01-36 | 1 | 129600 | 129600 | 3 Year | FortiCare Premium | Endpoint | On-premise
16 | VPN/ZTNA Client | Fortinet | FortiClient VPN/ZTNA 3Y (500ep) | FC2-10-EMS05-428-01-36 | 1 | 24969.6 | 24969.6 | 3 Year | FortiCare Premium | Endpoint
17 | Email Security | Fortinet | FortiMail-200F HW+3Y Base | FML-200F-BDL-640-36 | 2 | 14931 | 29862 | 3 Year | FortiCare Premium | Security | HA Pair
18 | WAF | Fortinet | FortiWeb-100F HW+1Y Standard | FWB-100F-BDL-934-12 | 2 | 25200 | 50400 | 1 Year | FortiCare Premium | Security | HA Pair
19 | Sandbox | Fortinet | FortiSandbox-500G | FSA-500G | 1 | 30000 | 30000 | N/A | FortiCare | Security
20 | DLP | Fortinet | FortiDLP Core 3Y (500-1999ep) | FC3-10-DLPEP-1097-02-36 | 500 | 162 | 81000 | 3 Year | FortiCare Premium | Endpoint | Per endpoint
21 | SIEM Appliance | Fortinet | FortiSIEM-2200G | FSM-2200G | 1 | 47040 | 47040 | N/A | FortiCare | SOC | All-in-one
22 | SIEM Collector | Fortinet | FortiSIEM-500G | FSM-500G | 2 | 15600 | 31200 | N/A | FortiCare | SOC | Remote collection
23 | SOAR | Fortinet | FortiSOAR Cloud Enterprise 3Y | FC-10-SRCLD-385-02-36 | 1 | 329911.2 | 329911.2 | 3 Year | FortiCare Premium | SOC
24 | NDR | Fortinet | FortiNDR-1000F HW+3Y | FNR-1000F-BDL-331-36 | 1 | 219300 | 219300 | 3 Year | FortiCare Premium | Security | AI-based
25 | Log Analyzer | Fortinet | FortiAnalyzer-150G HW+3Y | FAZ-150G-BDL-1263-36 | 1 | 26928.6 | 26928.6 | 3 Year | FortiCare Premium | SOC | 25GB/day
26 | Central Management | Fortinet | FortiManager-200G | FMG-200G | 1 | 19862.4 | 19862.4 | N/A | FortiCare | Management | 30 devices
27 | SASE | Fortinet | FortiSASE Standard 3Y | FC3-10-EMS05-547-02-36 | 200 | 288 | 57600 | 3 Year | FortiCare Premium | Remote Access | Per user
28 | Media Kiosk | OPSWAT | MetaDefender Kiosk | MDF-KIOSK | 4 | 0 | 0 | Annual | OPSWAT Support | Air-Gap | TBD
29 | HSM | Thales | Luna Network HSM | LUNA-HSM | 2 | 0 | 0 | N/A | Thales Support | Encryption | TBD
30 | OT Security | Nozomi | Nozomi Guardian | NOZOMI-GUARD | 2 | 0 | 0 | Annual | Nozomi Support | OT Network | TBD
31 | VA Scanner | Qualys | Qualys VMDR | QUALYS-VMDR | 1 | 0 | 0 | Annual | Qualys Support | Security | TBD
32 | GRC Platform | CyberArrow | CyberArrow GRC | CYBERARROW-GRC | 1 | 0 | 0 | Annual | CyberArrow Support | GRC | TBD
33 | Security Awareness | Proofpoint | Proofpoint SAT | PROOFPOINT-SAT | 1 | 0 | 0 | Annual | Proofpoint | Training | TBD
34 | DDoS Protection | A10 | A10 Thunder TPS | A10-TPS | 2 | 0 | 0 | N/A | A10 Support | Internet Edge | TBD
35 | Packet Broker | Gigamon | Gigamon GigaVUE | GIGAMON-GVUE | 2 | 0 | 0 | N/A | Gigamon Support | Network | TBD
[6 empty] | GRAND TOTAL (USD): | 2866519.8
* Items showing $0.00 require vendor quotation

## High Level Sizing
HIGH LEVEL SIZING — 200 to 4000 USER SCALE
Saudi Enterprise Cybersecurity Transformation Program ¦ NCA ECC / CSCC / ISO 27001 / NDMO Aligned
Technology Area | Component | 200 Users (Initial) | Model/SKU | Qty (Initial) | 4000 Users (Future) | Model/SKU (Future) | Qty (Future) | Sizing Rationale | Air-Gap Consideration
Firewall - DC Core | FortiGate NGFW | FG-400F (12 Gbps FW throughput) | FG-400F-BDL-950-36 | 2 | FG-1800F (75 Gbps FW throughput) | FG-1800F-BDL-950-36 | 2 | DC core handles E-W traffic; size for 10x growth | Same model supports air-gap zone
Firewall - Internet Edge | FortiGate NGFW | FG-200F (27 Gbps FW throughput) | FG-200F-BDL-950-36 | 2 | FG-900G (78 Gbps FW throughput) | FG-900G-BDL-950-36 | 2 | Internet breakout; sized for bandwidth growth | N/A for air-gap
Firewall - Distribution | FortiGate NGFW | FG-120G (25 Gbps FW throughput) | FG-120G-BDL-950-36 | 2 | FG-400F (68 Gbps FW throughput) | FG-400F-BDL-950-36 | 4 | East-West segmentation between zones | Dedicated pair for secure zone
Firewall - Branch | FortiGate NGFW | FG-60F (10 Gbps FW throughput) | FG-60F-BDL-950-36 | 4 | FG-120G (25 Gbps FW throughput) | FG-120G-BDL-950-36 | 10 | 1 per branch, SD-WAN
Access Switches | FortiSwitch PoE+ | FS-124F-FPOE (24-port) | FS-124F-FPOE | 10 | FS-248E-FPOE (48-port) | FS-248E-FPOE | 40 | 1 switch per 24 users, grow to 48-port | Same models for secure/air-gap
Core Switches | FortiSwitch 10G | FS-1048G (48x10G) | FS-1048G | 2 | FS-1048G (48x10G) | FS-1048G | 4 | Core aggregation layer | Dedicated pair for air-gap
Wireless APs | FortiAP Wi-Fi 6E | FAP-23JF-A | FAP-23JF-A | 20 | FAP-23JF-A | FAP-23JF-A | 80 | 1 AP per 25 users; density coverage | No wireless in air-gap
NAC | FortiNAC | FNC-CA-500F (15000 EP) | FNC-CA-500F | 1 | FNC-CA-500F (15000 EP) | FNC-CA-500F | 2 | Single appliance covers 200-4000 | HA for air-gap zone
VPN/ZTNA | FortiClient + FortiSASE | FC1 (25ep) + FortiSASE | FC1/FSASE | 1 | FC2 (500ep) + FortiSASE | FC2/FSASE | 1 | Scale endpoint licenses | N/A for air-gap
Endpoint EDR | FortiEDR | FC1 (25ep packs x8) | FC1-10-FEDR1 | 8 | FC2 (500ep) | FC2-10-FEDR1-352-01-36 | 1 | 200 initial → 500 pack | On-prem for air-gap
Email Security | FortiMail | FML-200F (HA pair) | FML-200F-BDL-640-36 | 2 | FML-400F (HA pair) | FML-400F-BDL-640-36 | 2 | 200F handles up to 600 users | Standalone in secure zone
SIEM | FortiSIEM | FSM-2200G (AIO) | FSM-2200G | 1 | FSM-3600G + Collectors | FSM-3600G | 1 | 25GB/day initial → 100GB+/day | Dedicated SIEM for air-gap
SOAR | FortiSOAR | Cloud Enterprise | FSR-Cloud | 1 | Cloud MT or On-Prem | FSR-Enterprise | 1 | Scale playbooks and users | On-prem for air-gap
Log Management | FortiAnalyzer | FAZ-150G (25GB/day) | FAZ-150G-BDL-1263-36 | 1 | FAZ-300G (100GB/day) | FAZ-300G | 2 | Scale with log volume | Dedicated for air-gap
Central Mgmt | FortiManager | FMG-200G (30 devices) | FMG-200G | 1 | FMG-410G (300+ devices) | FMG-410G | 1 | Scale with device count | Can manage air-gap FWs
PAM | FortiPAM | FPA-1000G (50 users) | FPA-1000G | 1 | FPA-1000G HA | FPA-1000G | 2 | 50 concurrent admin sessions | Mandatory for air-gap
DLP | FortiDLP | 200 endpoints | FortiDLP Core | 200 | 4000 endpoints | FortiDLP Core | 4000 | Per-endpoint licensing | Agent-based for air-gap
Sandbox | FortiSandbox | FSA-500G | FSA-500G | 1 | FSA-1500G | FSA-1500G | 1 | Scale with file volume | Critical for air-gap media scan
Media Security | OPSWAT MetaDefender | Kiosk x2 | MDF-KIOSK | 2 | Kiosk x4 + Vault | MDF-KIOSK | 4 | Air-gap file transfer | Core air-gap control
NDR | FortiNDR | FNR-1000F | FNR-1000F | 1 | FNR-1000F (HA) | FNR-1000F | 2 | Network anomaly detection | Deploy in secure zone

## Questions & Assumptions
QUESTIONS TO CUSTOMER & PROJECT ASSUMPTIONS
Saudi Enterprise Cybersecurity Transformation Program ¦ NCA ECC / CSCC / ISO 27001 / NDMO Aligned
# | Category | Type | Question / Assumption | Priority | Status | Response
1 | Network | Question | How many physical sites/branches require connectivity? | High | Open
2 | Network | Question | What is the current WAN/MPLS provider and bandwidth per site? | High | Open
3 | Network | Question | Is there an existing network infrastructure that must be retained or replaced? | High | Open
4 | Network | Question | What is the expected internet bandwidth at the main site? | Medium | Open
5 | Security | Question | Is there an existing SOC team or will SOC be outsourced to an MSSP? | Critical | Open
6 | Security | Question | What classification level does the air-gapped network require (Secret/Top Secret)? | Critical | Open
7 | Security | Question | Are there specific NCA ECC controls already implemented? | High | Open
8 | Security | Question | What is the current incident response maturity level? | Medium | Open
9 | Security | Question | Is OT/SCADA equipment present? If yes, provide asset inventory. | Critical | Open
10 | Air-Gap | Question | What is the approved method for software/patch updates in the air-gapped environment? | Critical | Open
11 | Air-Gap | Question | How many data transfer points exist between enterprise and air-gapped networks? | High | Open
12 | Air-Gap | Question | Is one-way data diode required for the air-gapped network? | High | Open
13 | Air-Gap | Question | What removable media types are approved (USB, CD, external HDD)? | High | Open
14 | Compliance | Question | Has the organization undergone a prior NCA ECC assessment? | High | Open
15 | Compliance | Question | Are there specific SAMA or sector-specific regulatory requirements? | High | Open
16 | Compliance | Question | Is there a Data Classification policy already in place per NDMO? | Medium | Open
17 | Identity | Question | What is the current directory service (AD, Azure AD, LDAP)? | High | Open
18 | Identity | Question | Is SSO/SAML federation required with external entities? | Medium | Open
19 | Sizing | Question | Confirm the 5-year user growth projection (200 → 4000)? | High | Open
20 | Sizing | Question | What is the expected number of servers, VMs, and containers? | High | Open
21 | Sizing | Question | What is the expected daily log volume (GB/day)? | Medium | Open
22 | Sizing | Question | How many concurrent VPN/remote access users are expected? | Medium | Open
23 | General | Assumption | All pricing is based on 3-year subscription terms unless noted | High | Confirmed
24 | General | Assumption | Fortinet is the strategic vendor for network and security infrastructure | High | Confirmed
25 | General | Assumption | Customer will provide rack space, power, and cooling at all sites | Medium | Assumed
26 | General | Assumption | Professional services and implementation labor are excluded from BOM | Medium | Assumed
27 | General | Assumption | Air-gapped network requires dedicated, physically separated infrastructure | Critical | Assumed
28 | General | Assumption | HA (Active-Passive or Active-Active) is required for all critical security controls | High | Assumed
29 | General | Assumption | The customer has or will obtain necessary NCA/SAMA licenses and approvals | High | Assumed
30 | General | Assumption | Network cabling (copper/fiber) infrastructure is in place or will be provided by customer | Medium | Assumed